## Sheet1
Issue # | Summary of Tasks | Links | Estimate (mins) | Coding Effort (mins) | Non-Coding Effort (mins) | Total Time (mins) | Estimator | Implementors
1 | Setup draft Bottles4College announcements page | https://github.com/cycle5ense/cycle5ense/issues/1 | 20 min | 20 min | 20 min | 40 min | rileyherra | rileyherra | https://github.com/cycle5ense/cycle5ense/issues/1
2 | Setup basic layout for entire website | https://github.com/cycle5ense/cycle5ense/issues/2 | 40 min | 25 min | 0 min | 25 min | danilk09 | danilk09 | https://github.com/cycle5ense/cycle5ense/issues/2
3 | Setup draft Find Nearest Bin page | https://github.com/cycle5ense/cycle5ense/issues/3 | 15 min | 10 min | 0 min | 10 min | danilk09 | danilk09 | https://github.com/cycle5ense/cycle5ense/issues/3
4 | Setup draft Sorting Guide page | https://github.com/cycle5ense/cycle5ense/issues/4 | 30 min | 15 min | 10 min | 25 min | ungert | ungert | https://github.com/cycle5ense/cycle5ense/issues/4
5 | Setup draft Recycling Impact Statistics page | https://github.com/cycle5ense/cycle5ense/issues/5 | 60 minutes | 27 minutes | 5 minutes | 32 minutes | jslagazo | jslagazo | https://github.com/cycle5ense/cycle5ense/issues/5
6 | Setup draft Map page | https://github.com/cycle5ense/cycle5ense/issues/6 | 30 min | 15 min | 10 min | 25 min | ungert | ungert | https://github.com/cycle5ense/cycle5ense/issues/6
7 | Create add pin page | https://github.com/cycle5ense/cycle5ense/issues/7 | 15 minutes | 8 minutes | 9 minutes | 17 minutes | Joshua Au | Joshua Au | https://github.com/cycle5ense/cycle5ense/issues/7
9 | Plan/setup data model/database | https://github.com/cycle5ense/cycle5ense/issues/9 | Completed with various pin issues and user profile page | Completed with various pin issues and user profile page | Completed with various pin issues and user profile page | Completed with various pin issues and user profile page |  |  | https://github.com/cycle5ense/cycle5ense/issues/9
10 | Create pin object | https://github.com/cycle5ense/cycle5ense/issues/10 | 30 minutes | 24 minutes | 9 minutes | 33 minutes | Joshua Au | Joshua Au | https://github.com/cycle5ense/cycle5ense/issues/10
11 | Fix Node.js 20 deprecated failure | https://github.com/cycle5ense/cycle5ense/issues/11 | Completed with issue 28 | Completed with issue 28 | Completed with issue 28 | Completed with issue 28 |  |  | https://github.com/cycle5ense/cycle5ense/issues/11
12 | Deploy Nextjs Application to Vercel | https://github.com/cycle5ense/cycle5ense/issues/12 | 60 min | 60 min | 30 min | 90 min | danilk09 | danilk09 | https://github.com/cycle5ense/cycle5ense/issues/12
13 | Box for map on map page | https://github.com/cycle5ense/cycle5ense/issues/13 | Complete with issue 7 | Complete with issue 7 | Complete with issue 7 | Complete with issue 7 | ungert | ungert | https://github.com/cycle5ense/cycle5ense/issues/13
14 | Map Pins | https://github.com/cycle5ense/cycle5ense/issues/14 | Completed with issue 7 | Completed with issue 7 | Completed with issue 7 | Completed with issue 7 | ungert | ungert | https://github.com/cycle5ense/cycle5ense/issues/14
15 | Pin Popup Package | https://github.com/cycle5ense/cycle5ense/issues/15 | finished with issue 14 | finished with issue 14 | finished with issue 14 | finished with issue 14 | ungert | ungert | https://github.com/cycle5ense/cycle5ense/issues/15
16 | Figure out Map API | https://github.com/cycle5ense/cycle5ense/issues/16 | 1 hour | 30 min | 15 min | 45 min | ungert | ungert | https://github.com/cycle5ense/cycle5ense/issues/16
17 | Adjust announcements, sorting guide, and recycling statistics pages to conform to selected layout/theme | https://github.com/cycle5ense/cycle5ense/issues/17 | 20 min | 15 min | 8 min | 23 min | Joshua Au | Joshua Au | https://github.com/cycle5ense/cycle5ense/issues/17
18 | Adjust bin map to conform to selected layout/theme | https://github.com/cycle5ense/cycle5ense/issues/18 | Completed with various map related issues | Completed with various map related issues | Completed with various map related issues | Completed with various map related issues |  |  | https://github.com/cycle5ense/cycle5ense/issues/18
19 | Update Seed | https://github.com/cycle5ense/cycle5ense/issues/19 | Completed with issue 28 | Completed with issue 28 | Completed with issue 28 | Completed with issue 28 |  |  | https://github.com/cycle5ense/cycle5ense/issues/19
21 | Create Announcement Object | https://github.com/cycle5ense/cycle5ense/issues/21 | 30 minutes | 17 minutes | 12 minutes | 29 minutes | Joshua Au | Joshua Au | https://github.com/cycle5ense/cycle5ense/issues/21
22 | Create landing page | https://github.com/cycle5ense/cycle5ense/issues/22 | 60 minutes | 43 minutes | 0 minutes | 43 minutes | jslagazo | jslagazo | https://github.com/cycle5ense/cycle5ense/issues/22
23 | Setup landing page | https://github.com/cycle5ense/cycle5ense/issues/23 | Closed as duplicate of issue-22 | Closed as duplicate of issue-22 | Closed as duplicate of issue-22 | Closed as duplicate of issue-22 |  |  | https://github.com/cycle5ense/cycle5ense/issues/23
24 | Design logo | https://github.com/cycle5ense/cycle5ense/issues/24 | 30 min | 5 min | 40 min | 45 min | rileyherra | rileyherra | https://github.com/cycle5ense/cycle5ense/issues/24
25 | Update information and graphics on Sorting Guide page | https://github.com/cycle5ense/cycle5ense/issues/25 | 60 min | 45 min | 30 min | 75 min | rileyherra | rileyherra | https://github.com/cycle5ense/cycle5ense/issues/25
26 | Add count up component to recycling impact statistics page | https://github.com/cycle5ense/cycle5ense/issues/26 | 30 min | 20 min | 30 min | 50 min | rileyherra | rileyherra | https://github.com/cycle5ense/cycle5ense/issues/26
27 | Cleanup current project for preparation of transitioning to M2 | https://github.com/cycle5ense/cycle5ense/issues/27 | 30 min | 0 min | 20 min | 20 min | danilk09 | danilk09 | https://github.com/cycle5ense/cycle5ense/issues/27
28 | Update test files | https://github.com/cycle5ense/cycle5ense/issues/28 | 40 min | 20 min | 30 min | 50 min | danilk09 | danilk09 | https://github.com/cycle5ense/cycle5ense/issues/28
31 | Setup admin sign in page | https://github.com/cycle5ense/cycle5ense/issues/31 | 30 minutes | 18 minutes | 4 minutes | 22 minutes | jslagazo | jslagazo | https://github.com/cycle5ense/cycle5ense/issues/31
32 | Create login page | https://github.com/cycle5ense/cycle5ense/issues/32 | Completed from prior issues. tied to issue 40 and 37 | Completed from prior issues. tied to issue 40 and 37 | Completed from prior issues. tied to issue 40 and 37 | Completed from prior issues. tied to issue 40 and 37 |  |  | https://github.com/cycle5ense/cycle5ense/issues/32
33 | Make statistics page use local data | https://github.com/cycle5ense/cycle5ense/issues/33 | finished with issues 34, 45 | finished with issues 34, 45 | finished with issues 34, 45 | finished with issues 34, 45 |  |  | https://github.com/cycle5ense/cycle5ense/issues/33
34 | Create form for users | https://github.com/cycle5ense/cycle5ense/issues/34 | finished with issue 45 | finished with issue 45 | finished with issue 45 | finished with issue 45 | ungert | ungert | https://github.com/cycle5ense/cycle5ense/issues/34
36 | Update footer | https://github.com/cycle5ense/cycle5ense/issues/36 | 35 minutes | 30 minutes | 43 minutes | 73 minutes | jslagazo | jslagazo | https://github.com/cycle5ense/cycle5ense/issues/36
37 | Direct Sign In/Up Buttons to Sign In/Up Pages | https://github.com/cycle5ense/cycle5ense/issues/37 | 20 min | 10 min | 10 min | 20 min | danilk09 | danilk09 | https://github.com/cycle5ense/cycle5ense/issues/37
38 | Streamline announcements page | https://github.com/cycle5ense/cycle5ense/issues/38 | 30 min | 12 min | 6 min | 18 min | Joshua Au | Joshua Au | https://github.com/cycle5ense/cycle5ense/issues/38
39 | make edit pins cleaner | https://github.com/cycle5ense/cycle5ense/issues/39 | finished with issue 14 | finished with issue 14 | finished with issue 14 | finished with issue 14 | ungert | ungert | https://github.com/cycle5ense/cycle5ense/issues/39
40 | Update Navbar for user specific pages | https://github.com/cycle5ense/cycle5ense/issues/40 | Done in conjunction with issue-37 |  |  |  | danilk09 | danilk09 | https://github.com/cycle5ense/cycle5ense/issues/40
41 | Fix navbar breakpoints | https://github.com/cycle5ense/cycle5ense/issues/41 | 15 min | 5 min | 5 min | 10 min | danilk09 | danilk09 | https://github.com/cycle5ense/cycle5ense/issues/41
42 | Implement landing page's admin URL redirection | https://github.com/cycle5ense/cycle5ense/issues/42 | 10 minutes | 9 minutes | 2 minutes | 11 minutes | jslagazo | jslagazo | https://github.com/cycle5ense/cycle5ense/issues/42
43 | Streamline add pin process | https://github.com/cycle5ense/cycle5ense/issues/43 | 20 min | 8 min | 2 min | 10 min | danilk09 | danilk09 | https://github.com/cycle5ense/cycle5ense/issues/43
44 | Update auth pages color scheme | https://github.com/cycle5ense/cycle5ense/issues/44 | 15 min | 10 min | 2 min | 12 min | rileyherra | rileyherra | https://github.com/cycle5ense/cycle5ense/issues/44
45 | Create user signed in page | https://github.com/cycle5ense/cycle5ense/issues/45 | 120 minutes | 60 minutes | 15 minutes | 75 minutes | ungert | ungert | https://github.com/cycle5ense/cycle5ense/issues/45
46 | Create an Edit Announcement page | https://github.com/cycle5ense/cycle5ense/issues/46 | 45 min | 15 min | 15 min | 30 min | Joshua Au | Joshua Au | https://github.com/cycle5ense/cycle5ense/issues/46
47 | Update admin page | https://github.com/cycle5ense/cycle5ense/issues/47 | 30 minutes | 20 minutes | 5 Minutes | 25 Minutes | ungert | ungert | https://github.com/cycle5ense/cycle5ense/issues/47
48 | Adjust footer visual to match overall website theme | https://github.com/cycle5ense/cycle5ense/issues/48 | 40 minutes | 19 minutes | 11 minutes | 30 minutes | jslagazo | jslagazo | https://github.com/cycle5ense/cycle5ense/issues/48
49 | User Password Update | https://github.com/cycle5ense/cycle5ense/issues/49 | 10 minutes | 5 minutes | 2 minutes | 7 minutes | ungert | ungert | https://github.com/cycle5ense/cycle5ense/issues/49
51 | Add pins to map | https://github.com/cycle5ense/cycle5ense/issues/51 | 180 min | 60 min | 300 min | 360 min | ungert | ungert | https://github.com/cycle5ense/cycle5ense/issues/51
52 | Create a feedback form | https://github.com/cycle5ense/cycle5ense/issues/52 | 5 min |  | 5 min | 5 min | danilk09 | danilk09 | https://github.com/cycle5ense/cycle5ense/issues/52
53 | Share website to people | https://github.com/cycle5ense/cycle5ense/issues/53 | 10 min |  |  |  | Everyone | Everyone | https://github.com/cycle5ense/cycle5ense/issues/53
54 | Add alternative information to Manoa Bin Map page | https://github.com/cycle5ense/cycle5ense/issues/54 | 120 minutes | 31 minutes | 25 minutes | 56 minutes | jslagazo | jslagazo | https://github.com/cycle5ense/cycle5ense/issues/54
55 | Add bin identification/reference images to sorting guide | https://github.com/cycle5ense/cycle5ense/issues/55 | 30 min | 30 min | 16 min | 46 min | rileyherra | rileyherra | https://github.com/cycle5ense/cycle5ense/issues/55
56 | Update button colors | https://github.com/cycle5ense/cycle5ense/issues/56 | 20 min | 15 min | 10 min | 25 min | rileyherra | rileyherra | https://github.com/cycle5ense/cycle5ense/issues/56
57 | Reorganize navbar tabs | https://github.com/cycle5ense/cycle5ense/issues/57 | 10 min | 3 min | 0 min | 3 min | Joshua Au, rileyherra | Joshua Au, rileyherra | https://github.com/cycle5ense/cycle5ense/issues/57
58 | Update form tables | https://github.com/cycle5ense/cycle5ense/issues/58 | 25 min | 20 min | 5 min | 25 min | danilk09 | danilk09 | https://github.com/cycle5ense/cycle5ense/issues/58
59 | Add confirmation question | https://github.com/cycle5ense/cycle5ense/issues/59 | 30 min | 20 min | 15 min | 35 min | danilk09 | danilk09 | https://github.com/cycle5ense/cycle5ense/issues/59
60 | Update admin pages user list | https://github.com/cycle5ense/cycle5ense/issues/60 | 15 mins | 10 min | 2 min | 12 min | ungert | ungert | https://github.com/cycle5ense/cycle5ense/issues/60
61 | OPTIONAL: Specify what was recycled | https://github.com/cycle5ense/cycle5ense/issues/61 | Optional (never done) | Optional (never done) | Optional (never done) | Optional (never done) |  |  | https://github.com/cycle5ense/cycle5ense/issues/61
62 | Fix background | https://github.com/cycle5ense/cycle5ense/issues/62 | Finished with issue-64 | Finished with issue-64 | Finished with issue-64 | Finished with issue-64 | rileyherra | rileyherra | https://github.com/cycle5ense/cycle5ense/issues/62
63 | Add Users | https://github.com/cycle5ense/cycle5ense/issues/63 | 30 min | 25 min | 5 min | 30 mins | ungert | ungert | https://github.com/cycle5ense/cycle5ense/issues/63
64 | Fix random bugs | https://github.com/cycle5ense/cycle5ense/issues/64 | 60 min | 70 min | 20 min | 90 min | danilk09 | danilk09 | https://github.com/cycle5ense/cycle5ense/issues/64
65 | Reorganize Announcements | https://github.com/cycle5ense/cycle5ense/issues/65 | 30 min | 12 min | 20 min | 32 min | Joshua Au | Joshua Au | https://github.com/cycle5ense/cycle5ense/issues/65
66 | Resolve navbar text bug | https://github.com/cycle5ense/cycle5ense/issues/66 | 60 minutes | 5 minutes | 26 minutes | 31 minutes | jslagazo | jslagazo | https://github.com/cycle5ense/cycle5ense/issues/66
67 | Fix Bottles4College Announcements page | https://github.com/cycle5ense/cycle5ense/issues/67 | 10 min | 20 min | 10 min | 30 min | rileyherra | rileyherra | https://github.com/cycle5ense/cycle5ense/issues/67
68 | Improve landing page | https://github.com/cycle5ense/cycle5ense/issues/68 | 10 min | 11 min | 4 min | 15 min | rileyherra | rileyherra | https://github.com/cycle5ense/cycle5ense/issues/68
69 | Fix recycling date entry | https://github.com/cycle5ense/cycle5ense/issues/69 | 25 minutes | 7 minutes | 7 minutes | 14 minutes | jslagazo | jslagazo | https://github.com/cycle5ense/cycle5ense/issues/69
70 | Add more announcements | https://github.com/cycle5ense/cycle5ense/issues/70 | 10 min | 0 min | 12 min | 12 min | Joshua Au | Joshua Au | https://github.com/cycle5ense/cycle5ense/issues/70
1 (github.io repo) | Finish home page setup for the cycle5ense.github.io repo | https://github.com/cycle5ense/cycle5ense.github.io/issues/1 | 60 min | 40 min | 10 min | 50 min | danilk09 | danilk09
5 (github.io repo) | Update home page | https://github.com/cycle5ense/cycle5ense.github.io/issues/5 | 30 min | 35 min | 10 min | 45 min | rileyherra | rileyherra
6 (github.io repo) | Update home page | https://github.com/cycle5ense/cycle5ense.github.io/issues/6 | 30 min | 30 min | 10 min | 40 min | danilk09 | danilk09
7 (github.io repo) | Update home page | https://github.com/cycle5ense/cycle5ense.github.io/issues/7 | 40 min | 10 min | 20 min | 30 min | danilk09 | danilk09

## Sheet2
Team Member | Software Development Experience (Months) | How was coding effort tracked? | How was non-coding effort tracked?
Joshua Au | 5 | Google Stopwatch | Best guess
Riley Herradura | 5 | Check clock start/end time | Best guess
Danil Knight | 12 | Best guess | Best guess
Julius Lagazo | 5 | Google Stopwatch | Google Stopwatch
Tyler Unger | 5 | Best guess | Best guess